## Sheet1
Connecticut Conversion Project Equipment Inventory
Equipment Location
Part Number | Item Name | Total Ordered Units | Total Received Units | Variance to be receieved | PO/SO/PR | Arpin | WG | TX | Madurai | Chenai | Canada | TN | NJ | CLC | Comment
61-0784-30 | Retailer Pro Terminal | 3223 | 815 | 2408 | 111372 | 800 | 4 | 1 | 1 | 3 | 1 | 1 | 1
53-0680-01E | Retailer Pro Printer | 3223 | 20 | 3203 | 111372
74-1432-01E | External 2D barcode reader (includes charging cradle, wireless) - Model DS2278 | 3223 | 858 | 2365 | 111372 |  | 858
24-2000-01E | Rtlr PRO(FLEX 2.0) - Domestic (Retailer Pro) Peripheral Stand | 3223 | 0 | 3223 | 111372
61-0901-45-CM | Winchecker | 3135 | 0 | 3135 | 111380 |  | 30
16-2108-569E | Winchecker Base | 3135 | 1710 | 1425 | 111380
51-1884-04E | Wincheck Radio Module | 3135 | 0 | 3135 | 111380
61-0762-06E | Wincheck Terminal Module | 3135 | 0 | 3135 | 111380
61-2000-22 | VCU For Keno | 1570 | 0 | 1570
61-0883-19-CM | GT28 Terminal (cashless-ready, P200 not installed) | 206 | 2 | 204 |  |  | 2
N/A | Dell 22 Monitor - P2222H, 54.6cm (21.5") | 2980 | 2980 | 0 |  | 2970 | 10 | [7 empty] | 10 units delivered to QA in WG.
N/A | CS-IGT GLOBAL SOLUTIONS CORP-OEM-C2G 2m HDMI to DVI Adapter Cable-Digital DVI-D (6.6ft)-2m HDMI to DVI Cable-2 meter-6 F | 2980 | 2910 | 70
N/A | CS-IGT GLOBAL SOLUTIONS CORP-OEM-C2G 2m HDMI to DVI Adapter Cable-Digital DVI-D (6.6ft)-2m HDMI to DVI Cable-2 meter-6 F | 200 | 200 | 0
N/A | Samsung BE43T-H BET-H Pro TV Series - 43" LED-backlit LCD | 2 | 2 | 0 | 4500278302 |  | 2
N/A | Samsung BE43T-H BET-H Pro TV Series - 43" LED-backlit LCD Keno Monitor | 1035 | 1035 | 0 |  | 1035
N/A | VCE VGA Female to Female Adapter SVGA Coupler HD15 Mini Gender Changer VGA Cable Extender | 1200 | 1165 | 35 |  |  | 1165
N/A | VGA to HDMI Cable, Benfei VGA to HDMI 6 Feet Cable with Audio Support and 1080P Resolution - VGA Input to HDMI Output | 1100 | 0 | 1100
11-5115-302E | Peripheral stand extension for Retailer Pro Terminal | 3000 | 0 | 3000
10-2369-01E x4 | Peripheral stand extension for Retailer Pro Terminal | 3000 | 0 | 3000
11-5079-302E | Peripheral stand extension for Retailer Pro Terminal | 50 | 0 | 50
N/A | CT press playslip proofs – 8 games 60lb paper | 8 | 8 | 0 |  |  | 8
46-2435-01 | Programmed SSD M.2 SATA3 MLC 32GB MTS400, with NX04 version of FW (for GT28) | 10 | 0 | 10
61-1981-02 | Terminal Retailer Select Connecticut | 250 | 0 | 250
74-1404-01E | VCU Mounting Brkt | 1600 | 0 | 1600
50-0335-01E | ASSY VFD USB PORT-POWERED GT1200 | 250 | 250 | 0 |  |  | 250